## Tabelle1
PROJEKT MILESTONES 2017 | Jan | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
First check with the NA: 31st of January | bar: Jan
Second check with the NA: 16th of March | bar: March
Writing the application, submission deadline: 29th of March | bar: Jan to March
Waiting for the result | bar: April to July
preparing the kick-off-meeting (with create) | bar: July to Sept
Kick-off-meeting in Maribor/1st meeting | bar: Sept
Content team: designing and structuring the course contents (8 modules) (IO 1) | bar: Oct to Dec
create: assisting the content team and demonstrating the cBook (WBT) | bar: Oct to Dec
Virtual meeting 1: Storyboards. Design & Structure for the Modules | bar: Nov
PROJEKT MILESTONES 2018 | Jan | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Virtual meeting 2: First introduction to the cBook | bar: Jan
content team: developing the course contents (8 modules) (IO 2) | bar: Jan to June
create: giving feedback and assisting, production of teaser and website | bar: Jan to June
Virtual meeting 3: First experiences with the cBook, final modules & further meetings | bar: April
Virtual meeting 4: First experiences with the cBook, chapter 1 to 4, outlook Valencia | bar: May
mid term meeting 1 in Valencia: presenting the course contents (8 modules) | bar: June
final feedback on module 1 and proofread | August: proofread
final feedback on module 2 and proofread | Sept: proofread
final feedback on module 3 and proofread | Oct: proofread
final feedback on module 4 and proofread | Nov: proofread
final feedback on module 5 and proofread | Dec: proofread
final feedback on module 6 and proofread | bar: Dec
Virtual meeting 5: Feedback on intro dialogues, didactical concept, work with the cBook | bar: Oct
PROJEKT MILESTONES 2019 | Jan | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
proofread
giving feedback on module 7 and proofread | Feb: proofread
giving feedback on module 8 and proofread | March: proofread
Virtual meeting 6: Completion of all chapters, financing & first outlook Opatija | bar: Jan
Virtual meeting 7: Completion of all chapters & draft programme Opatija | bar: March
create: production of the cBook (O4 - A1) | bar: March to June
content team: assisting the process, production of presentational videos/intros | bar: March to June
mid term meeting 2 in Opatija: presenting the final course, discussing the evaluation | bar: May
testing and evaluation phase of the course/cBook (online parts of modules) | bar: July to Nov
Virtual meeting 8: Testing of the cBook & first outlook Assisi | bar: Sept
Virtual meeting 9: Testing of the cBook & programme Assisi | bar: Oct
create: implementation of changes in the cBook | bar: Nov to Dec
Final meeting: presenting the final course; evaluation of the project, dissemination | bar: Dec
Content team: Writing the Manual for the iLab (IO 3) & Teacher Training Assessment | bar: July to Dec
PROJEKT MILESTONES 2020 | Jan | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
create: implementation of changes | bar: Jan to Feb
Content team: Writing the Manual for the iLab | bar: Jan to Feb
Virtual meeting 10: Wrap Up of the iLab & Teacher Training Assessment | bar: Jan
Virtual meeting 11: Final virtual meeting, project management issues | bar: Feb