## Tabelle1
PROJEKT MILESTONES 2017 | Jan | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
First check with the NA: 31st of January
Second check with the NA: 16th of March
Writing the application, submission deadline: 29th of March
Waiting for the result
preparing the kick-off-meeting (with create)
Kick-off-meeting in Maribor/1st meeting
Content team: designing and structuring the course contents (8 modules) (IO 1)
create: assisting the content team and demonstrating the cBook (WBT)
Virtual meeting 1: Storyboards. Design & Structure for the Modules
PROJEKT MILESTONES 2018 | Jan | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
Virtual meeting 2: First introduction to the cBook
content team: developing the course contents (8 modules) (IO 2)
create: giving feedback and assisting, production of teaser and website
Virtual meeting 3: First experiences with the cBook, final modules & further meetings
Virtual meeting 4: First experiences with the cBook, chapter 1 to 4, outlook Valencia
mid term meeting 1 in Valencia: presenting the course contents (8 modules)
final feedback on module 1 and proofread | [7 empty] | proofread
final feedback on module 2 and proofread | [8 empty] | proofread
final feedback on module 3 and proofread | [9 empty] | proofread
final feedback on module 4 and proofread | [10 empty] | proofread
final feedback on module 5 and proofread | [11 empty] | proofread
final feedback on module 6 and proofread
Virtual meeting 5: Feedback on intro dialogues, didactical concept, work with the cBook
PROJEKT MILESTONES 2019 | Jan | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
proofread
giving feedback on module 7 and proofread |  | proofread
giving feedback on module 8 and proofread |  |  | proofread
Virtual meeting 6: Completion of all chapters, financing & first outlook Opatija
Virtual meeting 7: Completion of all chapters & draft programme Opatija
create: production of the cBook (O4 - A1)
content team: assisting the process, production of presentational videos/intros
mid term meeting 2 in Opatija: presenting the final course, discussing the evaluation
testing and evaluation phase of the course/cBook (online parts of modules)
Virtual meeting 8: Testing of the cBook & first outlook Assisi
Virtual meeting 9: Testing of the cBook & programme Assisi
create: implementation of changes in the cBook
Final meeting: presenting the final course; evaluation of the project, dissemination
Content team: Writing the Manual for the iLab (IO 3) & Teacher Training Assessment
PROJEKT MILESTONES 2020 | Jan | Feb | March | April | May | June | July | August | Sept | Oct | Nov | Dec
create: implementation of changes
Content team: Writing the Manual for the iLab
Virtual meeting 10: Wrap Up of the iLab & Teacher Training Assessment
Virtual meeting 11: Final virtual meeting, project management issues